# SECTION 01270 (01 22 00)

## UNIT PRICES

GENERAL

SECTION INCLUDES

Measurement and payment criteria applicable to portions of the Work performed under a unit price payment method.

Defect assessment and non-payment for rejected work.

AUTHORITY

Measurement methods delineated in the individual specification sections complement the criteria of this section.  In the event of conflict, the requirements of the individual specification section govern.

Take all measurements and compute quantities.  The Project Consultant and Owner will verify measurements and quantities.

Assist by providing necessary equipment, workers, and survey personnel as required.

UNIT QUANTITIES SPECIFIED

Estimated quantities indicated on Document 00410-Bid Form, Document 00436-Schedule of Unit Prices or individual specification sections are for bidding and contract purposes only.  Quantities and measurements supplied or placed in the Work and verified by the Project Consultant and Owner determine payment.

If the actual Work requires the same or fewer quantities than those quantities indicated, provide the required quantities at the unit sum/prices contracted.

If the actual work requires more quantity than those quantities indicated, the contract sum shall be adjusted by Change Order, prior to commencement of additional work.

MEASUREMENT OF QUANTITIES

Measurement Devices:

Weigh Scales:  Inspected, tested and certified by the applicable Florida or Broward County department within the past year.

Platform Scales:  Of sufficient size and capacity to accommodate the conveying vehicle.

Metering Devices:  Inspected, tested and certified by the applicable Florida department within the past year.

Measurement by Weight:  Concrete reinforcing steel, rolled or formed steel or other metal shapes shall be measured by handbook weights.  Welded assemblies shall be measured by handbook or scale weight.

Measurement by Volume:  Measured by cubic dimension using mean length, width and height or thickness.

Measurement by Area:  Measured by square dimension using mean length and width or radius.

Linear Measurement:  Measured by linear dimension, at the item centerline or mean chord.

Stipulated Sum/Price Measurement:  Items measured by weight, volume, area, or linear means or combination, as appropriate, as a completed item or unit of the Work.

PAYMENT

Payments shall be for actual qualities, not estimated quantities.

Payment Includes:  Full compensation for all required labor, Products, tools, equipment, plant, transportation, services and incidentals; erection, application or installation of an item of the Work; overhead, profit, and taxes.

Final payment for Work governed by unit prices shall be made on the basis of the actual measurements and quantities accepted by the Project Consultant multiplied by the unit sum/price for Work which is incorporated in or made necessary by the Work.  Final contract sum shall be adjusted by Change Order to reflect actual qualities for unit price items.

DEFECT ASSESSMENT

Replace the Work, or portions of the Work, not conforming to specified requirements.

If, in the opinion of the Project Consultant and Owner, it is not practical to remove and replace the Work, the Project Consultant shall direct one of the following remedies:

The defective Work may remain, but the unit sum/price will be adjusted to a new sum/price at the discretion of the Owner.

The defective Work shall be partially repaired to the instructions of the Project Consultant, and the unit sum/price shall be adjusted to a new sum/price at the discretion of the Owner.

The individual specification sections may modify these options or may identify a specific formula or percentage sum/price reduction.

The authority of the Project Consultant and Owner to assess the defect and identify payment adjustment, shall be final.

NON-PAYMENT FOR REJECTED PRODUCTS

Payment shall not be made for any of the following:

Products wasted or disposed of in a manner that is not acceptable.

Products determined as unacceptable before or after placement.

Products not completely unloaded from the transporting vehicle.

Products placed beyond the lines and levels of the required Work.

Products remaining on hand after completion of the Work.

Loading, hauling and disposing of rejected Products.

SCHEDULE OF UNIT PRICES

Refer to:

Document 00410, Bid Form.

Document 00436, Schedule of Unit Prices.

PRODUCTS-Not Used

EXECUTION-Not Used

END OF SECTION