# SECTION 01290 (01 29 00)

## PAYMENT PROCEDURES

- GENERAL

- SECTION INCLUDES

    - Procedures for preparation and submittal of applications for payment.

    - RELATED DOCUMENTS

    - Document 00435-Schedule of Values.

    - Document 00436-Schedule of Unit Prices

    - Document 00520-Agreement Form.

    - Document 00700-General Conditions of the Contract:  For Contract Payments, Withholding Payments to Contractor, and Retainage procedures.

    - Section 01250-Contract Modification Procedures.

    - Section 01270-Unit Prices.

    - Section 01320-Construction Progress Documentation.

    - Section 01330-Submittal Procedures.

    - Section 01770-Closeout Procedures.

    - FORMAT

    - Submit requests for payment on Document 01290a-Application for Payment and Document 00435-Schedule of Values (as a continuation/detail sheet).

    - Contractor’s electronic media driven forms, which replicate the Owner’s standard forms, may be utilized when pre-approved by the Owner and Project Consultant and when required.

    - For each item, provide a column for listing each of the following:

    - Item Number.

    - Project Manual Section Number.

    - Description of work.

    - Scheduled Values.

    - Work Completed From Previous Applications.

    - Work Completed This Application.

    - Materials Presently Stored To Date.

    - Total Completed and Stored to Date.

    - Percentage of Completion.

    - Balance to Finish.

    - Retainage.

    - PREPARATION OF APPLICATIONS

    - Present required information in typewritten or computer generated form.

    - Execute certification by original signature of authorized officer.

    - Use data from approved Schedule of Values.  Provide dollar value in each column for each line item for portion of work performed and for stored products.

    - Entries shall match current data of Schedule of Values, Construction-Schedule, and other reports substantiating the Contractor’s progress.

    - List each authorized Change Order as an extension on Document 00435-Schedule of Values, listing Change Order number and dollar amount as for an original item of Work.

    - Prepare Application for Final Payment as specified in Section 01770-Closeout Procedures.

    - SUBMITTAL PROCEDURES

    - Submit 3 copies of each Application for Payment.

    - Submit an updated Construction Schedule with each Application for Payment.

    - Payment Period:  Submit at intervals stipulated in the Agreement.

    - Personally deliver or transmit to the Project Consultant by means ensuring receipt within 24 hours or less.  Verify receipt.

    - SUBSTANTIATING DATA

    - Submit data justifying dollar amounts requested for payment on the Document 01290a-Application for Payment.  Include as a minimum:

    - Description of stored materials, storage place, evidence of inspection by the Project Consultant, and verification that the Contractor’s purchase order amounts reconcile with the corresponding line items submitted for stored materials on the Application for Payment.

    - Copies of Document 01320a-Weekly Progress Reports for the respective payment period with copies of Contractor’s Daily Log not yet submitted under provisions of Section 01320.

    - A complete accounting of all payments made to Subcontractors and the balances owed to the Subcontractors with each Application For Payment submitted by the Contractor.

    - Dollar Value/Time Graphs:  Provide graphs as required by Document 00700-General Conditions, Article 9, and Section 1320, 1.4, C, 2.

    - Upon request, submit data (or allow inspections) verifying:

    - Daily regular and continuous updating of Project Record Documents.

    - Timely payment of subcontractors and suppliers.

    - Copies of acquired authorizations and licenses from governing authorities for current performance of the Work.

    - Listing of subcontractors and principal suppliers and fabricators (including documentation of any applicable licensure and or journeymen workforce supervision).

    - Evidence of Drug-Free Workplace certification, safety programs, prohibition of illegal aliens, and other workforce requirements of the Contract Documents.

    - Records concerning the dates of delivery of materials, lengths of time materials have been stored, and the time remaining until such materials are incorporated into the Work.

    - Other evidence as shall be required, at the discretion of the Owner and Project Consultant, to verify the progress and quality of the Work.

    - Provide 1 copy of data with cover letter for each copy of submittal.  Show application number and date, and line item by number and description.

    - PRODUCTS - Not Used

    - EXECUTION - Not Used

END OF SECTION