# SECTION 01630 (01 66 00)

## PRODUCT SUBSTITUTION PROCEDURES

GENERAL

SECTION INCLUDES

General Requirements.

Submittals.

Project Consultant’s Action.

Conditions.

Compliance with the Contract Documents.

RELATED DOCUMENTS

Document 00200-Instruction To Bidders.

Document 00520-Agreement Form.

Section 01250-Contract Modification Procedures.

Section 01610-Basic Product Requirements.

Section 01620-Product Options.

Document 01630a-Contractor’s Substitution Request.

GENERAL REQUIREMENTS

Substitutions:  Requests for changes in products, materials, equipment, and methods of construction required by Contract Documents proposed by the Contractor after award of the Contract are considered requests for "substitutions".  The following are not considered substitutions:

Substitutions requested by Bidders during the proposal period, and accepted prior to award of Contract, are considered as included in the Contract Documents and are not subject to requirements specified in this Section for substitutions.

Revisions to Contract Documents requested by the Owner or Project Consultant.

Specified options of products and construction methods included in Contract Documents.

The Contractor's determination of and compliance with governing regulations and orders issued by governing authorities.

The Contractor’s unilateral incorporation of non-specified products, materials and equipment into the Work.

The Contractor’s unilateral incorporation of products, materials and equipment, which do not conform to the requirements of the Contract Documents into the Work.

SUBMITTALS

Substitution Request Submittal:  Submit 3 copies of all substitution requests to the Project Consultant on Document 01630a-Contractor’s Substitution Request.

Include the information and documentation required on Document 01630a and other information necessary for an evaluation by both the Owner and the Project Consultant.

The burden of proof of the merit of the proposed substitution is upon the Contractor.

Substitution requests deemed incomplete or incorrect by the Project Consultant will be disapproved.

The Owner's decision, based upon recommendations of the Project Consultant, of approval or disapproval of a proposed substitution shall be final.

Requests for substitution will be considered if received within 30 days after receipt of Document 00550-Notice to Proceed.  Requests received more than 30 days after receipt of Document 00550-Notice to Proceed may be considered or rejected at the discretion of the Project Consultant.

Identify the product, or the fabrication or installation method to be replaced in each request.  Include related Specification Section and Drawing numbers.  Provide complete documentation showing compliance with the requirements for substitutions, and the following information, as appropriate:

Product Data, including Drawings and descriptions of products, fabrication and installation procedures.

Samples, where applicable or requested.

A detailed comparison on the same page of significant qualities of the proposed substitution with those of the Work specified.  Significant qualities may include elements such as size, weight, durability, performance and visual effect.  All differences in products shall be noted.

A detailed description of the effect the proposed substitution will have on LEED for Schools project requirements?

Coordination information, including a list of changes or modifications needed to other parts of the Work and to construction performed by the Owner and separate Contractors that will become necessary to accommodate the proposed substitution.

A statement indicating the substitution's effect on the Contractor's Construction Schedule compared to the schedule without approval of the substitution.  Indicate the effect of the proposed substitution on overall Contract Time.

Cost information, including a proposal of the net change, if any in the Contract Sum.

Certification by the Contractor that the substitution proposed: in every significant respect to that required by the Contract Documents, and that it shall:

Shall be equal to or better in every significant respect to specified material or product, and shall perform adequately in the intended application.

Provide the same or greater warranty for the substitution as for the specified product.

Provide the same required fire rating for the substitution as for the specified product.

Coordinate installation and make changes to other Work, which may be required for the Work to be complete with no additional costs to Owner.

Include the Contractor’s waiver of rights to additional payment or time that may subsequently become necessary because of the failure of the substitution to perform adequately.

PROJECT CONSULTANT'S ACTION

Within 7 days of receipt of the request for substitution, the Project Consultant will request additional information or documentation necessary for evaluation of the request.

Within 14 days of receipt of the request, or one week of receipt of the additional information or documentation, which ever is later, the Project Consultant will notify the Contractor of the Owner’s acceptance or rejection of the proposed substitution.

If a decision on use of a proposed substitute cannot be made or obtained within the time allocated, use the product specified by name.

Acceptance:

Acceptance will be in the form of Document 01250f-Project Consultant’s Supplemental Instructions for those accepted substitutions, which do not alter the Contract Sum or Time.

Acceptance will be in the form of a Change Order for those accepted substitutions, which alter the Contract Sum or Time.

PRODUCTS

CONDITIONS

The Contractor's substitution request will be received and considered by the Project Consultant and Owner when one or more of the following conditions are satisfied as determined by the Project Consultant:

Substitution Request is timely, fully documented and properly submitted.

The request is directly related to an "or approved substitute" clause or similar language in the Contract Documents for which the Contract Documents do not prescribe a particular remedy

The specified product or method of construction is no longer available.  The request will not be considered if the product or method cannot be provided as a result of the Contractor’s failure to pursue the Work promptly or coordinate activities properly.

The Owner has deemed the specified products or methods are no longer suitable or appropriate for incorporation into the Work.

A substantial advantage is offered the Owner, in terms of cost, time, energy conservation or other considerations of merit, after deducting offsetting responsibilities the Owner may be required to bear.  Additional responsibilities for the Owner may include additional compensation to the Project Consultant for redesign and evaluation services, increased cost of other construction by the Owner or separate Contractors, and similar considerations.

The specified item fails to comply with building code requirements.

The manufacturer or fabricator declares a specified product unsuitable for the use intended and refuses to warrant its installation.

Substitution requests, which do not, at the Project Consultant’s discretion, meet the criteria specified above, will be returned without action except to record noncompliance with these requirements.

Where a proposed substitution involves more than one contractor or the work of the Owner, the Contractor shall cooperate with the other contractors or Owner’s personnel involved to coordinate the Work, provide uniformity and consistency, and to assure compatibility of products.

COMPLIANCE WITH CONTRACT DOCUMENTS

The Contractor's submittal and Project Consultant's acceptance of Shop Drawings, Product Data or Samples that relate to construction activities not complying with the Contract Documents shall not constitute an acceptable or valid request for substitution, nor does it constitute approval.

Replacement of products, materials and equipment not specified or not complying with the Contract Documents is the sole responsibility of the Contractor.

EXECUTION-Not Used

END OF SECTION