BID DOCUMENT PROCEDURE FOR HARD BIDS

- Project Manager (or consultant) completes Division 0 and Division 1 for the project @ Phase III 50%.

- Document Management reviews index and drawing list in Division 0 and Division 1 @ Phase III 50%.

- Project Manager reviews Division 0 and Division 1 @ Phase III 50% submittal for accuracy, executes the checklist, and directs Consultant to make the revisions.

- Project Manager verifies the completeness of the required revisions in the Phase III 100% documents.

- Project Manager submits to Design Services.

- Design Services retains Division 1 for review and forwards Division 0 to Contracts @ Phase III 100%.

- Contracts and Document Management review Divisions 0 and Division 1 respectively @ Phase III 100% and provide comments to the Project Manager.

- Project Manager coordinates all revisions, compiles the bid document package consisting of construction drawings and project manual (including Divisions 0 – 17) and submits to Design Services.

- Document Management notifies Contracts and Project Manager when bid documents are ready.

- Contracts provide Document 00101 to the Project Manager and Document Management with the scheduled dates of advertisement.

- Project Manager transmits the completed bid package to Document Management a minimum of eight (8) working days prior to the first advertisement date (Document 00101 – Advertisement for Bids).

- Document Management prepares and checks the bid package.

- The bid package is sent by Document Management to applicable printer at least three (3) working days prior to the first bid advertisement date.

- Applicable printing firm provides reproduction, bidding services and issues bid documents to prospective bidders.

- Printer returns original bidding documents, and provides to the Document Management, five (5) copies of the bidding documents.

- Applicable printing firm provides Document Management with a list of bidders and Document 00215 (Application for Bid documents).

- The bid is advertised per SREF and Board Policy.

- Document Management posts bid advertisement and addenda to Demandstar.com; receives, logs, and distribute RFI’s; sends addenda to applicable printing firm and SBBC staff; and printer distributes addenda to plan holders.