## Grid Data
IT Project Status Report - 4-16-2007
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Canceled |  | 9/27/2004 | 6/30/2009
ETS05006 County Wide Summit on Technology Learning and Economic Development | This project focuses on holding a Regional Summit on Technology, Learning and Economic Development for the 21st Century. This summit explores linkages for a Citywide Integrated Information Technology System in support of learning and economic development to enhance the connectivity among home, school and community. | 9/27/2004 | 5/17/2005 | 100% | Canceled | CLOSED - pmo 3-22-05 Project was canceled 11-15-04 | Gieseking Linda | ETS | Gieseking Linda | Section XII.CAP8
FIN06001 Enterprise Resource Planning | Evaluate and implement a comprehensive Enterprise Resource Planning (ERP) solution for the district, based on business process audit and interoperability with related applications. The solution would encompass financial management, budget, purchasing, human resources management (including the automated collection of staff attendance and labor data), facilities management, asset management, materials management, construction management, transportation, and customer resource management applications. Additionally it should provide a data warehouse to support the ERP data and be integrated to the existing student data warehouse. | 12/21/2004 | 6/30/2009 | 100% | Canceled | SAP Implementation - Canceled -pmo 12-8-2006 | Zacharias Ken | Finance | Grimm Melissa | Section X.ADDS1
Closed |  | 5/9/2003 | 5/1/2007
ARS05001 School and Department Based Technology Support | This project focuses on the IT organizational and developmental needs at schools and departments. It proposes to develop, and implement a technology support staffing plan that addresses the technical needs for all schools and departments with emphasis on both support and integration. | 9/29/2004 | 3/23/2005 | 100% | Closed | CLOSED - pmo 3-23-2005 | Gieseking Linda | Area Superintendents | Gregg Sam | Section V.ODS1
ARS05002 Meaningful Budget Conferences | In order to make budget conferences more meaningful, allocate more time and include individual schools' needs. Area Superintendents, Area Directors, Area ESE Coordinators, Area Business Analysts, Instructional Staffing Representatives, and a Title One Representative will be scheduled to attend the budget conferences. | 1/3/2005 | 3/30/2005 | 100% | Closed | CLOSED - pmo 5-25-2005 | Moquin Denis | Area Superintendents | Smith Ron | SP.FN6
ARS05003 Qualified Instructors for School Budgeting | Make the budget training more effective by having qualified instructors who can explain the philosophies of budgeting, not just the "how to's". | 1/3/2005 | 9/15/2005 | 100% | Closed | CLOSED pmo-10-5-2005 | Moquin Denis | Area Superintendents | Colton Sue | SP.FN7
ARS05004 HRMS Positon Control | The Position Control process currently in place was designed and implemented in response to the RFP requirements of the HR/Payroll implementation in 2000. These business processes requirements resulted in a cumbersome process that resides, for the most part, outside the SAP software. Recent staffing changes at the Area Offices and the decentralization of the control processes has significantly improved the efficiency of the Position Control effort. The review committee will determine if additional changes are needed and, if so, when would be the appropriate time to make them, i.e., should we wait for the mandatory upgrade to the SAP system to make best use of SAP's latest functionality or is the need important enough to address the changes in 4.6B. | 1/3/2005 | 3/21/2005 | 100% | Closed | CLOSED - pmo 5-12-2005 | Zielinski Paul | Area Superintendents | Remy Claude | SP.HR1
ARS05005 HRMS Separations | The Area Business Analyst (Business Project Manager) would like to identify an automated way for a payroll contact to notify the Payroll Department to "Lock" the employee's record once notified that the employee has terminated. Currently they are required to place a call to Payroll Department after the local payroll contact has stopped payment for the employee at their location. The current method is highly ineffective. | 1/3/2005 | 3/21/2005 | 100% | Closed | CLOSED - pmo 11-15-05 | Zielinski Paul | Area Superintendents | Cupo Rick | SP.HR3
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
ARS05006 Check Sequencing | Paychecks and Pay Advices should be delivered to locations in alphabetical order and in one group. The SAP System is delivering the documents in alphabetical order but is separating checks from advices. This project represents a cost saving approach, so as not to print Pay Advices on expensive watermarked paper. As the District converts to mandatory Direct Deposit, there will only be one set of alphabetized documents delivered to locations. | 2/10/2004 | 7/29/2004 | 100% | Closed | CLOSED - pmo 5-12-2005 | Zielinski Paul | Area Superintendents | Cupo Rick | SP.HR8
COS05001 Program Level Planning | Develop a system-wide method to manage the interdependencies across program-level planning initiatives. Utilize a budgeting process that analyzes the TCO (total cost of ownership) of each program and align those programs with District strategic plans and budgets. Include district level measures of performance. | 11/12/2004 | 7/22/2005 | 100% | Closed | CLOSED - pmo 7-23-2005 | Schmaus Becky | Chief of Staff | Terrel Nancy | Section IX.DSSP3
COS05003 Grants Training | The Grants Administration & Government Programs Department will provide training and information to allow schools to obtain more competitive grants. This includes, but is not limited to how to find and monitor available grants, the purpose of the grant opportunities, and how to respond to grant applications. | 7/30/2004 | 8/15/2005 | 100% | Closed | CLOSED - pmo 10-5-2005 | Moquin Denis | Chief of Staff | Mandley Frank | SP.FN8
CUR05002 Technology Standards Articulation and Alignment Across the Curriculum Through Beep | Fully integrate the National Education Technology Standards for students into the Broward curriculum standards and district curriculum frameworks for all levels in all discipline areas. | 5/7/2004 | 1/2/2007 | 100% | Closed | CLOSED - pmo 2-21-2007 | Jeanine Gendron | Curriculum | Gendron Jeanine | Section II.CA2
CUR05005 Online and Computer Based Staff Development | Continue to deliver training in required proficiencies through a variety of training delivery methods, including online and computer-based delivery, video-based tutorials, just in time training, classroom coaching and mentoring. | 5/9/2003 | 8/1/2005 | 100% | Closed | CLOSED - 4-5-2006 | Jeanine Gendron | Curriculum | Gendron Jeanine | Section VI.SDT3
CUR05006 Digital Learning Environment Study | Define, implement and evaluate learning environments at the elementary and secondary levels to support digital learning, virtual learning and community outreach for all students, including students with disabilities and students who have limited proficiency in English. These learning environments are based upon scientifically researched best practice teaching and learning strategies. | 2/6/2004 | 9/30/2005 | 100% | Closed | CLOSED - pmo 4-5-2006 | Jeanine Gendron | Curriculum | Gendron Jeanine | Section IV.TLE1
CUR05007 Special Populations | Explore, develop, pilot and expand scientifically researched, best practice teaching/learning strategies to address the unique needs of the district's students with disabilities through the integration of appropriate technologies. | 11/1/2004 | 5/1/2007 | 100% | Closed | CLOSED - pmo 10-26-2006 | Diamond Daryl | Curriculum | Kelly Leah | Section III.TLT5
ETS05004 Food Service Upgrade | Review the current Point of Sale (POS) system used in the Food & Nutrition department and recommend upgrade or replacement. | 3/4/2005 | 6/30/2005 | 100% | Closed | CLOSED - pmo 7-31-2006 | Moquin Denis | ETS | Moquin Denis | Section X.ADDS15
ETS05005 Data Warehouse Access Software Upgrade | Upgrade the data warehouse query, reporting and analysis tool (BRIO) with a version that supports current Web browsers on Macintosh and Windows computers to improve access to data. The new software, Hyperion Performance Suite, should allow for the creation of dashboard summary views that assist school and district administrators in monitoring school performance. | 1/3/2005 | 8/29/2005 | 100% | Closed | CLOSED - pmo 8-29-2005 | Stanley Jeff | ETS | Stanley Jeff | Section X.ADDS6
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
ETS05007 School and Work Day Continuity Plan | Study the implications of community connectivity to quantify issues of cost, user support, service quality expectations, security, equity, and protection. Continuation of the school day from home and off-site locations, access to ILS systems located in schools, and the Web, including delivery of training and support. | 1/3/2005 | 3/1/2007 | 100% | Closed | CLOSED - pmo 3-16-2007 | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI22
ETS05008 RFP Development and Funding Options | Continue to utilize E-Rate funding as build out-of-network and communication systems reaches completion. Research additional district facilities that could use E-rate and align with the annual E-rate funding cycle. Develop Request for Proposals and/or bids that are required for equipment and service purchases. | 10/15/2004 | 4/27/2005 | 100% | Closed | CLOSED - pmo 5-20-2005 | Coluzzi Angela | ETS | Coluzzi Angela | Section XI.CNI1
ETS05009 AS400 Consolidation | The AS/400s currently in the schools are 5 years old and are in need of replacement. This project will upgrade the district AS/400s in order to allow a centralized version of TERMS to run, thus eliminating the primary need for the AS/400 in the school. | 11/10/2004 | 9/12/2005 | 100% | Closed | CLOSED - pmo 9-12-2005 | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI8
ETS05010 Data Center Printers | The Computer Operations Center at Education Technology Services is replacing two IBM3900 high speed laser printers with newer models. The IBM4000 printer can produce 324 images per minute (IPM) in simplex/landscape mode. This is an increase of 90 IPM. The printers have the capability of creating a more readable page by providing higher print resolutions using IBM’s Print Quality Enhancement technology. New forms can be created in-house and existing forms easily modified using IBM Advanced Function Printing (AFP) architecture. AFP is currently used and fully supported by the new printers. The printers come with an Enhanced Operator Console utilizing an intuitive graphical user interface (GUI) that allows the computer operators to control the printer functions, monitor the printer operations and consumables usage, and resolve printer issues on-line. The procurement of these new printers will allow the Computer Operations Center to continue to meet the current printing demands of the School District and be prepared to handle future printing requirements. | 7/1/2004 | 6/30/2005 | 100% | Closed | CLOSED - pmo 7-5-2005 | Sullivan Brian | ETS | Sullivan Brian | Section XI.CNI19
ETS05011 Establish a School and Department Continuity Plan | Implement continuity plans for information systems at the school and department level. Integrate application owners, stakeholders, and constituents into the central data disaster recovery processes. The disaster recovery project was engaged to develop disaster recovery and business continuity plans to sustain information and systems supporting the critical processes in schools and departments. | 4/1/2005 | 3/2/2007 | 100% | Closed | CLOSED - pmo 2-21-2007 | Stanley Chuck | ETS | Fulop Ken | Section XI.CNI14
ETS05012 Central Software Distribution and Patch Management | Implement a centralized software distribution system to deliver applications and desktop images, manage licensing, and distribute updates. Integrate with single sign-on initiative. | 7/13/2005 | 3/5/2007 | 100% | Closed | CLOSED - pmo 2-21-2007 | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI24
ETS05016 Portable Building Network Connectivity | Complete expansion of communications infrastructure to all portable buildings to ensure the equity of network access to all students and staff. | 7/1/2004 | 10/12/2005 | 100% | Closed | CLOSED - pmo 2-13-2005 | Coluzzi Angela | ETS | Coluzzi Angela | Section XI.CNI9
ETS05021 Strategic Management System for the School District | Design, develop and implement a strategic management system (SMS) that includes processes, structures, and tools for monitoring the implementation of the Information Technology Blueprint and evaluating the impact on learning outcomes. This system will track schedules, resource allocations and fidelity to required program components. This project should be expanded to include a system that can be used throughout the district for strategic planning. | 9/10/2004 | 7/25/2005 | 100% | Closed | CLOSED - pmo 7-23-2005 | Schmaus Becky | ETS | Schmaus Becky | Section XIII.ME1
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
ETS05023 Establish a Project Management Office | Establish a project management office to align all implementation initiatives to the Sterling model of Plan, Do, Study and Act. The project management office oversees the implementation of projects to assure that project plans use performance measures that include customer satisfaction and student achievement. Implement a centralized office for the coordination, monitoring and control of all district initiatives to contribute to the successful completion of BCPS projects and provide a holistic understanding of project issues and dependencies. | 9/23/2004 | 3/1/2005 | 100% | Closed | CLOSED - pmo 3-15-2005 | Schmaus Becky | ETS | Schmaus Becky | Section XIII.ME3
ETS05025 Service Level Management | Provide the framework to develop and implement standards of service and IT service level agreements (SLA's). A SLA defines a level of service and responses to that service level are tracked. The goal is to increase the speed of service, to decrease the number of calls, and increase the satisfaction of the end users. At the end of a set time period, or a school year, the SLAs are examined to see how they can be made more responsive to the users. In addition, after the first SLAs are established, additional ones for the most widely used applications are created. This project installs automated "probes" to proactively monitor five mission-critical applications and to dynamically report performance levels via a "IT Service Catalog" website. | 11/3/2004 | 7/12/2006 | 100% | Closed | CLOSED - pmo 7-27-2006 | Baker Mary | ETS | Baker Mary | Section V.ODS2
ETS05027 Appoint District Continuity Project Manager | Establish a new position within ETS to manage Information Security and Continuity Planning. | 1/24/2005 | 5/20/2005 | 100% | Closed | CLOSED - pmo 5-20-2005 | Stanley Chuck | ETS | Stanley Chuck | SP.DR1
ETS05028 School and Department Checklist For Continuity Plan | Schools and Departments create site-based databases for local data. There is no consistent strategy for protecting this data in the event of data loss or disaster. This project establishes a checklist to assist schools in identifying vulnerabilities that should be considered when developing disaster recovery procedures. | 1/3/2005 | 4/29/2005 | 100% | Closed | CLOSED - pmo 5-31-05 | Stanley Chuck | ETS | Fulop Ken | SP.DR2
ETS05030 Mainframe Upgrade Project | The mainframe upgrade project evaluates and provides a framework for decisions relevant to the mainframe and central computing resources. The objective is to mitigate the mainframe demand problem over the last fiscal year quarter thus simplifying and clarifying the means to develop a strategy to upgrade, use and maintain the mainframe over the next several years. | 3/1/2004 | 3/29/2005 | 100% | Closed | CLOSED - pmo 5-19-2005 | Stanley Chuck | ETS | Kemp Joe | SP.MF1
ETS05031 Year End Load Reduction | The SAP Support Center successfully met all Year-End reporting requirements and timelines for the 2003 - 2004 school year. This included not only all internal reporting but the COST Report that is required for submission to the State of Florida. The CELT organization did provide an alternative Labor Report that can be run in those months when computing resources are being taxed and reporting deadlines are in risk. This alternative report does sacrifice a slight degree of accuracy and will only be used when necessary. To date, there has not been the need to utilize this alternative report. | 4/14/2004 | 5/24/2004 | 100% | Closed | CLOSED - pmo 5-12-2005 | Zielinski Paul | ETS | Zielinski Paul | SP.MF2
ETS05032 ReEstablish Technology Standards Committee | This committee will ensure interoperability of all elements of the system, to lower procurement costs, and to simplify maintenance, support, and asset management to reduce total cost of ownership. A designated standards committee with representatives from all district technology users was created to establish these standards and then monitor adherence to them on an ongoing basis. | 3/1/2004 | 4/27/2005 | 100% | Closed | CLOSED - pmo 6-2-2005 | Coluzzi Angela | ETS | Barrs Barbara | Section VII.SPMI1
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
ETS05033 Total Cost of Ownership | Develop a total cost of ownership (TCO) model for communication, computing, and network systems in order to understand clearly present and future cost of services to evaluate better proposed enhancements and generate cost/benefit analysis for administrative decisions. Develop a baseline TCO for the district. | 1/10/2005 | 8/12/2005 | 100% | Closed | CLOSED - pmo 8-22-05 | Baker Mary | ETS | Baker Mary | Section X.ADDS2
ETS05037 Compass Learning Odyssey Upgrade | Schools using the client-based CompassLearning Classic software will migrate to the web-based Odyssey software that can be run centrally from ETS and is accessed via our wide-area network. This removes the technical support requirement for the workstation and the server from the school and also allow for the integration of Odyssey with TERMS and our data warehouse. | 9/22/2004 | 8/30/2005 | 100% | Closed | CLOSED - pmo 8-30-2005 | Stanley Jeff | ETS | Stanley Jeff | ETS
ETS05039 Digital Divide | The Digital Divide program has a goal of eliminating the gap between people and communities who can make effective use of information technology and those who cannot. The vision is to develop a comprehensive program that aligns district resources with community and business partners to provide home computing capabilities to low-income families. The initial thrust will be to refurbish surplus SBBC computers and distribute them to Title I families, after they complete technology literacy training. The computers will have educational programs installed for the students. Second level training for parents will introduce internet access. | 10/11/2004 | 3/27/2006 | 100% | Closed | CLOSED - pmo 6-6-2006 | Baker Mary | ETS | Baker Mary | ETS
ETS05040 Transition Project Management | ETS05040 Transition Project Management Provide transition and implementation support to the Broward County Public Schools for the BETS Blueprint. Two major activities are provided. (1) Focus on gaining stakeholder understanding and support for the Blueprint. During this Phase, specific projects will be clearly defined, owners assigned, and projects delineated by time frames. (2) Focus on implementation of the specific projects, developing case data needed for continued implementation in future years, and monitoring/evaluating the progress of implementation. During this Phase direct assistance to assigned owners and leaders will be provided. | 8/2/2004 | 3/17/2005 | 100% | Closed | CLOSED - pmo 4-15-2005 | Pierre Winston | ETS | Pierre Winston | PHASE III
ETS05041 Memory Upgrade for Computers | Upgrade operating systems (MAC OS 10.3 and PC Win XP) and memory in all eligible computers throughout the District, to provide a district license to allow sites to bring all applicable platforms up to the same level. | 1/3/2005 | 12/8/2006 | 100% | Closed | CLOSED - pmo 12-8-2006 | Coluzzi Angela | ETS | Coluzzi Angela | Section IV.TLE5
ETS05042 Change Management | A change management process is defined as “the process of planning, coordinating, and monitoring changes affecting an organization’s computing resources (network, workstations, servers/mainframes and applications) in order to ensure availability, responsiveness and customer satisfaction”. This project defines and implements a technology change management process for the ETS department. | 10/5/2004 | 2/3/2005 | 100% | Closed | CLOSED - pmo 3-15-2005 | Baker Mary | ETS | Baker Mary | PHASE III
ETS05044 Support of Digital Learning Environment | The support of the digital learning environment includes a complete installation of an enterprise wireless network at each site. The one-to-one initiative includes the imaging, installation, and distribution of laptop computers for all students and teachers, in addition to on site installation and support of each site based server to support this ongoing project. | 4/13/2004 | 9/15/2005 | 100% | Closed |  | Coluzzi Angela | ETS | Coluzzi Angela | ETS
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
ETS05045 Broward Parentlink Project | ETS05045 Broward Parentlink Project The District acquired the Services of Parlant Technology’s ParentLink. This solution gives schools and departments the ability to: 1.Automatically deliver truancy notification calls to student’s homes. 2.Deliver phone and email messages about school functions and other non-emergency alerts. 3.Deliver phone and email messages concerning school or District emergency situations. This effort is being undertaken to assure policy and statute compliance; improve attendance and student achievement; improve school-home relations; and provide a tool for making emergency parent contacts. | 5/9/2003 | 6/2/2005 | 100% | Closed | CLOSED - pmo 6-2-2005 | Coluzzi Angela | ETS | Coluzzi Angela | ETS
ETS05046 Education Technology Plan | Develop and submit compliance documentation of the District's Educational Technology Plan to the Florida Department of Education. State-approved compliance documentation is required for the district to remain eligible for state and federal technology funding. The previously approved compliance document will be updated to align with the National Education Technology Plan, SBBC's Strategic Planning, and the Information Technology Blueprint. | 3/3/2005 | 10/21/2005 | 100% | Closed | CLOSED - pmo 11-30-05 | Baker Mary | ETS | Baker Mary | ETS
ETS05047 Customer Relationship Management CRM Implementation | This project focuses on the implementation of a new Customer Relationship Management (CRM) solution. MySAP CRM is a set of methodologies and software with CTI technology and Internet customer self-service capabilities that will provide the ETS Service Desk with the foundation for a more efficient team. | 4/11/2005 | 10/10/2005 | 100% | Closed | CLOSED - pmo 12-5-2005 | Gieseking Linda | ETS | Gieseking Linda | ETS
ETS05048 District Wireless Network Implementation | Enable BCPS Mobile users with Enterprise District Standard Wireless Network Equipment at all sites. | 6/16/2004 | 6/1/2005 | 100% | Closed | CLOSED - pmo 2-13-2005 | Coluzzi Angela | ETS | Coluzzi Angela | ETS
ETS05049 Student Technology Refresh | ETS05049 Student Technology Refresh Procure, and implement an effective technology equipment replacement plan. Equipment reaching the end of its useful life will be replaced in all Elementary, Middle, High, and Centers. Site specific location of the equipment would be transparent to the replacement cycle thus creating a more equitable process. The existing standard/bid will govern what equipment is purchased as replacement. | 2/4/2005 | 2/3/2006 | 100% | Closed | CLOSED - pmo 4-5-2006 | Coluzzi Angela | ETS | Coluzzi Angela | Section IV.TLE5
ETS06001-0 Project Knexus, Workplace for Education Pilot | KNEXUS, defined as the merging of knowledge with technology, is the management access system that will unify BCPS’s applications, information, and diverse databases through a single internet web page commonly known as a web portal. This “Workplace for Education” will provide BCPS administrators the ability to customize their gateway for the information that they need to support “No Child Left Behind” (NCLB) goals and requirements; access to information about their students; and access to information to improve their ability to manage their school. The Web portal content and applications will be tailored to specific job requirements in order to meet the diverse needs of all district personnel. The Project Knexus Pilot is a joint venture between BCPS and IBM. The pilot will leverage the WebSphere Portal Extend V5.1 capabilities which were developed during the initial February 2005 proof-of-concept (PoC) to establish a limited scope “Workplace Pilot” solution. The pilot will include 30 targeted users, to include principals, and guidance counselors, that will test capabilities and provide input for future project phases. The primary goal of the “Workplace Pilot” project will be integrating 4 applications into portlets: Virtual Counselor, TERMS, Hyperion and Class Size Projections. | 7/20/2005 | 11/9/2005 | 100% | Closed | CLOSED - pmo 10-20-2006 | Hineline Ed | ETS | Hineline Ed | ETS
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
ETS06001-1 Project Knexus, Workplace for Education Phase 1 | KNEXUS, defined as the merging of knowledge with technology, is the management access system that will unify SBBS’s applications, information, and diverse databases through a single internet web page commonly known as a web portal. SBBC administrators will have a customizable gateway for the information they need to support “No” Child Left Behind” (NCLB) goals and requirements. Web portal content and applications will be tailored to specific job requirements in order to meet the diverse needs of district personnel. The KNEXUS project will create a “Workplace for Education” that provides administrators access to information about their students and allows effective communication with students, parents, teachers, and other administrators to ensure that Adequate Yearly Progress (AYP) goals are met. The Project Knexus Phase 1 is a joint venture between BCPS and IBM. Phase 1 will leverage the WebSphere Portal Extend V5.1 capabilities which were developed during the initial Pilot to establish an enterprise ready “Workplace Solution” for School Administrators and Guidance Counselors. | 11/28/2005 | 5/22/2006 | 100% | Closed | CLOSED - pmo 10-20-2006 | Hineline Ed | ETS | Smith Ron | ETS
ETS06001-1A Knexus Communications Plan | The KNEXUS project will create a “Workplace for Education” that provides administrators access to information about their students and allows effective communication with students, parents, teachers, and other administrators to ensure that Adequate Yearly Progress (AYP) goals are met. A Communication/Knowledge Transfer element is part of the Change Management Plan. The purpose of the Project KNEXUS, Phase I Communications Plan is to provide an overall framework for managing and coordinating the wide variety of communications that will directly or indirectly take place as part of the implementation and rollout. It addresses communicators, audiences, messages, communication channels, feedback mechanisms and message timing, and creates a mapping between all six. This framework will ensure that Project KNEXUS provides relevant, accurate, and consistent information to the organization at all times. The purpose of the Project KNEXUS Training and Knowledge Transfer plan is to ensure that the user community utilizing Project KNEXUS and the Educational Technology IT group responsible for maintenance have adequate and properly focused training. It is important to understand the training needs of each stakeholder group, develop targeted training activities, and deliver content via the appropriate method. | 2/7/2006 | 5/31/2006 | 100% | Closed | CLOSED - pmo 10-20-2006 | Hineline Ed | ETS | Hineline Ed | ETS
ETS06002 District Wireless Implementation Phase 2 | Enable BCPS Mobile users with Enterprise District Standard Wireless Network Equipment at all sites. | 12/8/2005 | 7/31/2006 | 100% | Closed | CLOSED - pmo 7-31-2007 | Coluzzi Angela | ETS | Coluzzi Angela | ETS
ETS06004 Additions and Upgrades to School and District Conferencing Services | This project entails refresh and upgrade of district-wide video and audio conferencing, bridging, scheduling, and management systems along with video conferencing units in schools and departments. | 8/1/2005 | 4/6/2006 | 100% | Closed | CLOSED - pmo 2-13-2005 | Baker Mary | ETS | Baker Mary | Section IV.TLE2
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
ETS06005 ONE BROWARD NETWORK ASSESSMENT | This phase of the OneBroward project includes the assessment of the OneBroward Participant Organizations’ infrastructure and network assets that are currently in place. Determine and create a set of design assumptions for the OneBroward network infrastructure and services requirements can be based utilizing existing OneBroward participants' assets. A set of case studies will be developed to demonstrate the services and applications that can be offered by the integration of OneBroward participants network assets with other network technologies. The scope of this study will only include the following participants: School Board of Broward County (BECON and ETS), Broward County (Data Communications, Library, Public Works/Traffic), Universities (BCCC, FAU, FIU, NSU), Healthcare (Memorial Hospital System, North Broward Hospital District) and Utilities (FPL - Utlities & Fiber Scan Only, Comcast, BellSouth, MCI, SBC). | 12/26/2005 | 8/10/2006 | 100% | Closed | CLOSED - pmo 10-25-06 | Schmaus Becky | ETS | SchifferSimon Phyllis | ETS
ETS06006 Upgrade MeetingPlace Collaborative Tools | Upgrade existing MeetingPlace system to the newest 8106 hardware platform and install PC related servers for data, web and audio collaboration. This will provide a total 294 audio and data ports. | 4/4/2005 | 10/12/2006 | 100% | Closed | CLOSED - pmo 1-17-2007 | Baker Mary | ETS | Baker Mary | ETS
ETS06008 Customer Relationship Management System Phase 2 | Customer Resource Management (CRM) II seeks to increase the performance, functionality, and scope of the CRM system implemented during CRM Phase I. | 11/21/2005 | 11/9/2006 | 100% | Closed | CLOSED - pmo 2-21-2007 | Baker Mary | ETS | Baker Mary | ETS
ETS06009 TSSC Building Access Layer Upgrade | Replace existing access layer network hardware that is out of warranty with new proposed hardware. At the same time change the network environment from statically assigned IP addressing to geographically dynamic DHCP, reducing network management time. Re-patch existing patch cabling to reduce future support issues. | 1/18/2006 | 4/24/2006 | 100% | Closed | CLOSED - pmo 10-20-2006 | Coluzzi Angela | ETS | Coluzzi Angela | ETS
ETS06010 Network Integration Group - Active Directory (AD) Migration | Migrate users within the Network Integration group of ETS to the BROWARDSCHOOLS.LOCAL Active Directory (AD) structure. | 4/3/2006 | 6/1/2006 | 100% | Closed | CLOSED - pmo 6-1-2006 | Coluzzi Angela | ETS | Coluzzi Angela | ETS
ETS07001 Budget Forecast Committee Video Collaboration Upgrades | Install and configure desktop personal video conferencing systems and train the Budget Forecast Committee for members on their useage. | 6/15/2006 | 9/26/2006 | 100% | Closed | CLOSED - pmo 10-06-2006 | Baker Mary | ETS | Baker Mary | ETS
ETS07002 District IT Blueprint Review conducted by the CELT Corporation | The Blueprint review is comprised of 6 subprojects: 1. Review, Analyze and Upgrade SBBC’s implementation of the strategic Information Technology Blueprint/Plan. 2. Assess recent and proposed technology RFPs and contracts. 3. Review the cost benefit analysis, ROI and Total Cost of Ownership models used in the district. 4. Identify current/emerging needs and educational initiatives and assess the districts staff capacity to implement these. 5. Report the status of previous audits, exceptions and observations from Jan.2005-Oct.2006. 6. Assess the effectiveness of the districts use of Service Level Agreements for technology contracts. | 10/3/2006 | 3/21/2007 | 100% | Closed | CLOSED - pmo 3-16-2007 | Schmaus Becky | ETS | Schmaus Becky | ETS
ETS07004 Student Laptop Refresh 06_07 | This project will continue the retrofitting of existing classrooms to the new district educational specifications. This portion of the retrofitting would maintain the current refresh ratio of 1:6 students to mobile technology at appropriate school sites. | 8/2/2006 | 2/16/2007 | 100% | Closed | CLOSED - pmo 2-21-2007 | Coluzzi Angela | ETS | Coluzzi Angela | Section IV.TLE5
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
FAC05001 Technical Infrastructure for School Facilities | The goal is to provide an educational, technical, design, and material district standard that is provided to all internal and external architects, and contractors who provide a service to design, construct, install, and maintain the district's technology and energy management infrastructure. The overall mission is to ensure technological equity and energy efficiency throughout the district. The tactical objective is to ensure an updating and funding process that will keep the standards in alignment with the educational learning strategies and equipment defined by the Division of Curriculum & Instruction/Student Support. The current Generic Educational Specifications, Technical Specifications, Design and Material Standards are in alignment with the current educational strategies. It should be noted that this is not a project with a specific end date milestone but rather an on-going "living" process that is in need of refresh every time curriculum or energy management strategies change. | 1/3/2005 | 3/18/2005 | 100% | Closed | CLOSED - pmo 5-19-2005 | Coluzzi Angela | Facilities | Getz Tom | Section IV.TLE4
FAC05002 Technology Enhancement Upgrade and Refresh Plan | Initiate and fund effective technology equipment refresh plan. Equipment reaching the end of its useful life is replaced or removed once identified. The existing technology standards govern what equipment is procured as replacement. | 2/4/2005 | 6/17/2005 | 100% | Closed | CLOSED - pmo 6-17-2005 | Coluzzi Angela | Facilities | Getz Tom | Section IV.TLE5
FIN05001 HRMS Combine Use 6 and 0 | In order to assist principals in identifying their bottom line budgets with respect to labor costs, combine the Use 6 and Use 0 labor reports into one report. | 8/3/2004 | 1/25/2005 | 100% | Closed | CLOSED - pmo 5-25-2005 | Moquin Denis | Finance | Turner Jane | SP.FN1
FIN05002 SA IA Review | Bring current support and instructional allocation models up to modern times. Train principals that the new models are not mandatory but only a guide. | 9/9/2004 | 12/22/2004 | 100% | Closed | CLOSED - pmo 5-26-2005 | Moquin Denis | Finance | Turner Jane | SP.FN10
FIN05003 Budget Communications | Revise the current process that requires an approval process prior to budget letters being sent to affected users. | 4/15/2004 | 12/21/2004 | 100% | Closed | CLOSED - pmo 5-26-2005 | Moquin Denis | Finance | Moquin Denis | SP.FN11
FIN05004 Reduce Number of Required Signatures | Review the District's authorization forms and applicable School Board Policies with the intention of reducing the number of signatures required. | 8/3/2004 | 4/21/2005 | 100% | Closed | CLOSED - pmo 5-24-2005 | Moquin Denis | Finance | Robinson Henry | SP.FN2
FIN05005 Change Budget Schedules Preparation | Change the schools' budget preparation meetings to occur in February and coincide with the scheduling process and boundary data. | 9/7/2004 | 2/28/2005 | 100% | Closed | CLOSED - pmo 5-26-2005 | Moquin Denis | Finance | Turner Jane | SP.FN4
FIN05006 Year End Closing | Shorten the time it takes to close the fiscal year by condensing year end closing process and providing yearend reports earlier. | 1/3/2005 | 5/13/2005 | 100% | Closed | CLOSED - pmo 5-17-2005 | Moquin Denis | Finance | Grimm Melissa | SP.FN9
FIN05007 Financial Reports | Review financial reporting for schools and make modifications where necessary to expedite and clarify reports. | 3/19/2004 | 6/2/2005 | 100% | Closed | CLOSED - pmo 10-17-2005 | Moquin Denis | Finance | Turner Jane | SP.FN14
HRS05001 Conversion to district Wide Bi Weekly Payroll | The School District will re-engineer the current payroll processes to convert it into a bi-weekly payroll cycle for all employees. This causes a reduction in the number of payrolls processed from seven to two. This reduces workloads for both End-users and the Payroll Department. Employees not on a 12 month calendar will be given the option to receive a paycheck during their non-working calendar months. This assists employees with budgeting their personal finances, if they so choose. | 12/13/2004 | 8/1/2005 | 100% | Closed | CLOSED - pmo 7-31-2005 | Zielinski Paul | Human Resources | Suarez Marta | SP.HR5
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Closed |  | 5/9/2003 | 5/1/2007
HRS05003 Turn on Tracking | The SAP System has the capability to maintain an audit trail of activity on selected transactions. This allows for the creation, upon request, of all past changes to an Employee Record, including the nature of the change, when it was made, and who made the change. This tracking capability was initiated in the spring of 2004, and has not had any significant impact on systems performance to date. | 10/1/2004 | 12/14/2004 | 100% | Closed | CLOSED - pmo 5-12-2005 | Zielinski Paul | Human Resources | Suarez Marta | SP.HR10
HRS05006 HRMS PAF | The Personnel Action Form business processes needs a major overhaul. The Human Resource Division has agreed to address this need as part of the ERP System implementation and the HR/Payroll System upgrade to Enterprise. | 3/16/2005 | 5/18/2005 | 100% | Closed | CLOSED - pmo 6-2-2005 | Zielinski Paul | Human Resources | Suarez Marta | SP.HR2
HRS05007 HRMS Leaves | The Leaves department was established as part of the 2004-2005 organization chart. It serves as a central focus point to provide employees direction on leave alternative options and to process and monitor formal leave requests. | 3/31/2004 | 7/1/2004 | 100% | Closed | CLOSED - pmo 5-12-2005 | Zielinski Paul | Human Resources | Cochran Dan | SP.HR4
HRS05008 HRMS Retroactive Changes | The SAP System requires End-Users to establish a procedure to "set" a Control Record. This Control Record prevents retroactive adjustments from occurring in any preceding timeframe. The Finance Division has established a procedure to allow no more than one full year and the current year to be open to adjustments. The Control Record is "set" in the fall of each year by the SAP Support Center at the direction of the Director of Accounting. | 3/17/2004 | 4/21/2004 | 100% | Closed | CLOSED - pmo 6-3-2005 | Zielinski Paul | Human Resources | Suarez Marta | SP.HR7
HRS05009 HRMS ZA 71 Changes | The SAP System was successfully modified to allow Payroll Contacts at one location to "view-only" time entered for one of their employees at a different location. In addition, they now have the capability to make corrections to their time entries directly into the system without the need of involving third parties. The "tracking" allows an audit trail when, and if, necessary. A pilot was successfully conducted in October 2004 with a district-wide rollout occurring in November 2004. | 6/14/2004 | 11/18/2004 | 100% | Closed | CLOSED - pmo 5-12-2005 | Zielinski Paul | Human Resources | Suarez Marta | SP.HR9
STP05002-0 Strategic Management System for the School District Pilot | Develop, and implement a method for aligning and coordinating all major district plans (strategic plan, technology plan) including those recommended in this Information Technology Blueprint. Use the Sterling Plan, Do, Study, Act (PDSA) continuous improvement model as a backbone for all district-planning activities. | 5/2/2005 | 7/28/2006 | 100% | Closed | CLOSED - pmo 7-27-2006 | Schmaus Becky | Research and Evaluations | Zinn Judy | Section IX.DSSP1
STP05004 Distance Learning | Continue development of distance learning to enhance both work and learning environments. Conduct a total cost assessment that includes ancillary costs and benefits. Develop policies that help to move conferencing and distance learning more deeply into daily practices. | 1/10/2005 | 10/30/2006 | 100% | Closed | CLOSED - pmo 12-8-2006 | Diamond Daryl | Chief of Staff | SchifferSimon Phyllis | Section IV.TLE2
STP05005 Virtual Advanced Community Learning Centers | Expand concept for the development and implementation of Virtual Advanced Community Learning that will provide Broward County with online courses, training programs, independent/community study opportunities and staff development programs. Include integration with adult education programs. | 1/3/2005 | 8/15/2006 | 100% | Closed | CLOSED - pmo 7-13-2006 | Diamond Daryl | Curriculum | Miracola John | Section IV.TLE3
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
On Hold |  | 10/8/2004 | 7/9/2008
CUR05004 School and Community Technology Access Centers | Focus efforts of the Career, Technical and Adult/Community Education, district, and school leadership to provide community access to educational services/programs and technology required to effectively utilize the various web-based resources that are part of the Information Technology Blueprint. | 1/3/2005 | 12/20/2007 | 4% | On Hold | On Hold due to lack of funding | Diamond Daryl | Curriculum | Miracola John | Section XII.CAP4
ETS05003 Document Management System | Implement an Integrated Document Archival and Retrieval System (IDARS), to include a Distributed Output Management (DOM) system. To reduce redundancy and wasted time generating, retrieving, distributing, and archiving documents and forms, SBBC needs to investigate the benefits of implementing a document management system. | 1/13/2005 | 11/2/2007 | 5% | On Hold | On Hold - Funding not approved by Budget Forecast | Moquin Denis | ETS | Moquin Denis | Section X.ADDS3
ETS05026 Catalog Technology and Information Processes Procedures | Develop a comprehensive technology catalog of information processes and procedures with hierarchies and categories for easy access, and keyword search, to include an interactive web-based user access point for the management of the system. Review existing processes and procedures and propose to remove those that are duplicated or outdated. System will eventually be expanded to include all district processes and procedures as they relate to systems and technology. Align processes and procedures with user needs and business systems requirements. A unified, relevant catalog of processes and procedures will make a stronger connection between the strategic objectives of BCPS and the teachers, administrators and staff while easy access motivates compliance and provides clear directions for identified situations and circumstances. | 9/3/2007 | 7/9/2008 | 0% | On Hold | On Hold - Due to lack of Resources - 2-10-2006 | Baker Mary | ETS | Baker Mary | Section VIII.PP1
RAE05001 Online Assessment Tools | Procure (either develop or purchase) a Web-based, district-wide online assessment system utilizing valid and reliable test items that are aligned to district curriculum, state standards, and the statewide assessment (FCAT) and integrate the system with Curriculum Development and Implementation Management (CD/IM) System. Ensure that assessment results populate the diagnostic component of the AIP and are used to drive instruction. | 5/17/2005 | 6/24/2008 | 18% | On Hold | On Hold due to Lack of Funding - CELT doing RFP | Stanley Jeff | Research and Evaluations | Kraft Kimberly | Section II.CA4
RAE05002 Student Information Systems Review | Interview Key stakeholders to gather issues with TERMS and requirements for a student information system. Identify the additional databases developed by schools to supplement TERMS and develop requirements for a student information system RFP. | 10/8/2004 | 1/16/2007 | 21% | On Hold | ON HOLD - Due Lack of Funding | Stanley Jeff | Research and Evaluations | Eyerman Gina | Section X.ADDS4
STP05001 Community Access and Engagement Plan | For the Community Access and Engagement Plan to succeed, employees and the public need to be informed about the program and how it will specifically benefit all stakeholders. The Communications Plan will include the use of many established communications vehicles to achieve this purpose, including but not limited to community meetings, the District Web site, the news media, Communicating Across Broward (CAB), posters, flyers and perhaps newsletters, as appropriate. The Community Engagement piece will include, but is not limited to, soliciting the active involvement in the project from various community groups, businesses and the religious community. | 9/3/2007 | 4/18/2008 | 0% | On Hold | On Hold due to lack of Resources 2-10-2006 | Baker Mary | Chief of Staff | Bromery Keith | Section XII.CAP1
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Open |  | 4/30/2004 | 7/18/2008
COS05002 Catalog Equity Objectives | Establish and maintain a process system to ensure that technology resources are equitable and accessible to all students throughout the district as defined by the Citizens Concerned about our Children (CCC) settlement agreement. | 7/1/2004 | 7/6/2006 | 75% | Open |  | Coluzzi Angela | Chief of Staff | MartinOgburn Dildra | Section VIII.PP4
COS05004 E Mentoring | Establish a district-wide e-mentoring program that leverages the power of the Internet to electronically connect students with mentors in the school district and in the community. The e-mentor initiative will expand opportunities for individuals in the community to act as a resource for students. | 12/2/2004 | 6/20/2007 | 31% | Open |  | Diamond Daryl | Chief of Staff | SchifferSimon Phyllis | Section XII.CAP3
CUR05001 Comprehensive Approach for Building a CDIM System | BCPS continues the development of the CD/IM application. District leadership identifies the modules that are most important and/or of highest priority and focuses district resources (funding and manpower) on these components. This includes the development and implementation of tools which assure that administrators, teachers, students and parents have access to appropriate curriculum and instructional information to meet school achievement objectives. | 4/30/2004 | 10/30/2007 | 86% | Open |  | Jeanine Gendron | Curriculum | Gendron Jeanine | Section II.CA1
CUR05003 Curriculum and Technology Integration Approaches | Focus instruction at all levels in all disciplines toward appropriate instructional strategies including project-based learning, acceleration and independent practices. Support these approaches to teaching and learning with the development of scientifically researched best practice technology and curriculum integration strategies. Develop selection criteria for specific content/course applications. | 8/3/2004 | 7/24/2007 | 97% | Open |  | Jeanine Gendron | Curriculum | Gendron Jeanine | Section II.CA3
CUR05008 Transform Role of Library Media to IT | This project focuses on assuring that library media centers attain their full potential and play a leadership role in developing information literate students and lifelong learners. Emphasis is on staff, information literacy skills collaboratively taught, school climate, facilities, and resources. | 4/18/2005 | 9/26/2007 | 82% | Open |  | Jeanine Gendron | Curriculum | Gendron Jeanine | Section III.TLT8
CUR05009 Student Technology Internship Program STIP | Provide various mentoring, job shadowing, internship, and paid on-the-job training opportunities for students in the various IT related career and technical programs. Collaboration between the ETS Department and the schools will enhance the instructional programs, give students the opportunity to apply academic and technical competencies in the IT related jobs, and help to develop a cadre of trained IT workers for the district. | 11/4/2004 | 6/29/2007 | 87% | Open |  | Diamond Daryl | Curriculum | Miracola John | Section III.TLT3
ETS05013 Network Service Quality | Configure networking, communication, and computing processes toward a customer-oriented perspective to improve the quality of service delivery by establishing service-level agreements that focus on the customer’s expectations of service objectives. | 3/6/2006 | 8/23/2007 | 97% | Open |  | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI3
ETS05014 WAN Strategy | Establish a steering committee to develop a strategic plan to guide WAN development for the next five years. This plan should assess the opportunity for partnership with the county to develop a county-wide fiber backbone, the current deployment plan using BellSouth for fiber to the schools, and how an Instructional Television Fixed Service (ITFS) wireless capability might supplement capacity and provide redundancy. Consideration should be given to the potential E-Rate discounts for each of the approaches. Define capabilities, limitations, and benefits for deployment of both wired and wireless wide area networks. | 3/6/2006 | 11/28/2007 | 21% | Open | Starting 3-6-2006 | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI4
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Open |  | 4/30/2004 | 7/18/2008
ETS05015 Communications Systems Convergence | Assess the implications of convergence of communication systems and video distribution onto the data network. Study communication needs and the means for communication to align closely the technology capabilities with user requirements. Consider ways to consolidate technologies while improving capabilities and reducing costs. Create a strategic plan for migration of security, surveillance, and safety systems into the digital environment for facilities management and student transportation. | 2/6/2006 | 7/18/2008 | 63% | Open |  | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI5
ETS05017 Network Authentication | Continue to develop a comprehensive solution for network authentication, single sign-on and user management. Develop options that address service to Macintosh and Windows users, legacy applications, critical desktop applications, existing Macintosh and Windows servers and the existing AS/400 NT server cards. Develop a pilot implementation to test options and develop a final solution. Define exceptions to the single sign-on model including legacy applications and incompatible operating systems and develop migration plans for each. Implement the solution in all sites. | 4/1/2005 | 4/9/2007 | 47% | Open |  | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI10
ETS05018 ITFS Wireless Strategy | Assess wireless connectivity to schools and possibly to community. Make recommendations on the way reliable, high-bandwidth services should be delivered to schools. Explore microwave frequency Instructional Television Fixed Service (ITFS) as an enhancement or supplemental capability to the Wide-Area Network (WAN). | 4/3/2006 | 7/4/2008 | 30% | Open | Pending Pilot for ETS-06005-OneBrowardNetwork | Stanley Chuck | ETS | SchifferSimon Phyllis | Section XI.CNI11
ETS05020 Communication Continuity Plan | Develop a service continuity plan to provide communication services during crisis and disaster situations, and investigate linkages to homeland security issues. | 1/23/2006 | 12/7/2007 | 12% | Open |  | Stanley Chuck | ETS | Stanley Chuck | Section XI.CNI5
ETS05029 BCPS - Kronos Time Management Workforce | This project automates time management in several areas and improves payroll processing in other areas. Manual entry and duplicate entry will be eliminated and process improvements will simplify the handling of substitute teacher pay. (KRONOS) | 10/15/2004 | 4/26/2006 | 85% | Open |  | Zacharias Ken | ETS | Moquin Denis | SP.HR14
ETS06003 District-wide Electronic Gradebook Implementation | Implement an electronic gradebook at all schools. | 3/7/2005 | 7/9/2008 | 41% | Open | Pinnacle | Stanley Jeff | ETS | Stanley Jeff | ETS
ETS06007 Independent Devices Enabling Access (IDEA) | The school district, through its IT Blueprint projects, continues to embed eLearning opportunities more deeply into classrooms, schools, and departments creating ubiquitous teaching, learning, and work enviornments. Continuing in this direction, ETS will beta test a variety of hand held content storage devices including; but not limited to; iPonds, Sony PSP, Dell Axim, Archos DVR, and Palm Life Drive; to determine their ability to capture and deliver on demand audio and video content. This endeavor is being conducted to determine the educational and district-wide benefits that can be achieved through these technologies to enhance content delivery and storage capacities. | 4/3/2006 | 3/22/2007 | 92% | Open |  | Diamond Daryl | ETS | Diamond Daryl | ETS
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Open |  | 4/30/2004 | 7/18/2008
ETS06011 Blackboard eLearning District-Wide Pilot | Broward County Public Schools is extending its eLearning capacity to include various eLearning initiatives and programs which presently include: Broward Virtual University, Human Resource and Development (HRD),K-12 Instructional Technology initiatives, Sheridan's eLearning Broward, CTACE's online programs, and Broward Virtual Education's online middle and high school. The development of the necessary technical Blackboard infrastructure supporting these endeavors will seamlessly coordinate these initiatives with other IT projects. These projects include: Project Knexus Workplace for Education, the Independent Devices Enabling Access (IDEA) Project, and the District's Videostreaming Project. Blackboard eLearning District-wide Pilot will be developed, implemented, and evaluated to assist with and ensure the interoperability of the e-Commerce components, the Blackboard Content Management System, e-Portfolio Management, Virtual Hard Drive Management, Library Digital Asset Management, and the Blackboard Community System. | 4/17/2006 | 7/26/2007 | 73% | Open |  | Diamond Daryl | ETS | Diamond Daryl | Section IV.TLE2
ETS06012 Centralized Technical Support Upgrades | This project will provide upgrades that will enable the centralized ETS Help Desk and the MCTS Pool to better support schools and departments. | 6/7/2006 | 9/28/2007 | 80% | Open |  | Baker Mary | ETS | Baker Mary | Section V.ODS1
ETS06013 Accessing Video Content Through United Streaming | This project will align key stakeholders in developing and implementing a district-wide plan to deliver the newly acquired United Streaming video subscription for the 06-07 school year. | 7/7/2006 | 7/25/2007 | 78% | Open |  | Diamond Daryl | ETS | Diamond Daryl | ETS
ETS07003 Classroom Video Projector Project 06_07 | This project will begin the retrofitting of existing classrooms to the new district educational specifications. This portion of the project will provide schools with a projector per wireless cart as projected in the 05/06 Student Technology Refresh Project and delivered in accordance with that project. | 8/2/2006 | 3/30/2007 | 63% | Open |  | Coluzzi Angela | ETS | Coluzzi Angela | Section IV.TLE5
ETS07005 Teacher Laptop Refresh 06_07 | This project will continue the retrofitting of existing classrooms to the new district educational specifications. This portion will assist in providing schools identified by the Area Offices additional teacher laptops. | 8/2/2006 | 3/30/2007 | 78% | Open |  | Coluzzi Angela | ETS | Coluzzi Angela | Section IV.TLE5
HRS05002 Staff Development Planning and Management System | In order to better meet the growing staff development needs and improve services to teachers and approximately 15,000 other employees, a comprehensive and centralized Staff Development Management System is needed. Additionally, the Florida Standards for Professional Development System Evaluation Protocol require web-based resources to be accessible by District staff. This system includes such features as: user-friendly interface, 24-hours / 7 days a week availability,, ability to display the District's Staff Development Calendar, registration for staff development activities via the Internet, management of Professional Growth Plans (PGP) and opportunities for on-line staff development. Implementation and support requires a System Coordinator and a Customer Service Specialist. | 7/1/2004 | 6/12/2008 | 54% | Open |  | Diamond Daryl | HR Development |  | Section VI.SDT1
HRS06001 Highly Qualified Teacher Designation and Reporting Process | Create an automated process that will collate data from TERMS, SAP, and Data Warehouse that can be sent back to TERMS to report status of Broward County Public Schools' teachers as it relates to the Highly Qualified Teacher (HQT) designation specified by the NCLB Act. | 9/14/2005 | 10/9/2006 | 99% | Open |  | Diamond Daryl | Human Resources | Brito Becki | ETS
HRS07001 Highly Qualified Teacher Status - Phase II | This project is the second phase of the Highly Qualified Teacher Status reporting that will integrate all the necessary components including the HOUSSE documentation and in-field/out-of-field designation, enabling the school district to identify teachers. | 9/5/2006 | 6/1/2007 | 51% | Open |  | Diamond Daryl | Human Resources | Brito Becki | ETS
Project Name | Project Description | Start | Finish | % Complete | PMO STATUS | Comments | ETM | Sponsor | Business Manager | Source or Blue Print Section
Open |  | 4/30/2004 | 7/18/2008
SIU06002 Security Tracking & Response System (STAR) Fast Tracking Implementation | Johnson Controls and SISCO are joining efforts to implement the “FAST TRACK” security system in all schools in the District. This security system is a Security Tracking and Response system (STAR) that is a high-speed, photo capturing, visitor, volunteer, mentor pass system designed to replace the manual visitor logbooks and generic visitor passes being used today by many schools. STAR is a security identification system that gives site administrators a tool to control visitors that enter their school. By capturing the visitor’s photo, driver’s license or identification information the system will perform an automated check against national sexual offender databases, the Broward County Clerk of Courts database and the capacity to add additional databases in the future. A photo ID will be issued if the visitor is cleared. | 6/8/2005 | 3/20/2006 | 99% | Open |  | Stanley Chuck | Special Investigative Unit | Laverde Jose | ETS
User Name: Becky Schmaus
Timestamp: Monday, April 16, 2007 6:53:24 AM